## Export Summary
This document was exported from Numbers. Each table was converted to an Excel worksheet. All other objects on each Numbers sheet were placed on separate worksheets. Please be aware that formula calculations may differ in Excel.
Numbers Sheet Name | Numbers Table Name | Excel Worksheet Name
Template Retrospective
| Table 1 | Template Retrospective
Template Backlog
| Table 1 | Template Backlog

## Template Retrospective
Sprint Retrospective | Iteration | TEMPLATE
Project
Group
User Story | Task | Task Assigned to | Estimated Effort (in hours per person) | Actual Effort | Done | Notes
User wants to see his progress | main menu GUI | Kamron and Jahson | 2019-08-02 | 8 | NO
Initial
User wants to input habits + leaderboard | Formulaire of habits creation | Vlad | 2019-08-02 | 10 | Mostly
User wants to authorise better | Server authorisation in the right way | julius | 3 | 4 | YES
Developer wants to create in the database new features + testing all functionalities | Junit tests + new features code | Pablo and Paul | 9 | 10 | Mostly
Main Problems Encountered |  |  |  |  | NO
Problem 1 | Technial & git problems
Description | technical problems/learning java fx, organisational matters (different branches)
Reaction | We all agree to push more things
Problem 2 | Communication misconduct
Description | There was some problems like different designs of GUI due to lack of communication
Reactions | Communication is a must
Adjustments for next Sprint Plan | push more to work in to updated versions | more communication between server and client and between anyone working on a common task

## Template Backlog
Sprint Backlog | Iteration | TEMPLATE
Project
Group
Amount of hours
Member
Estimated amount of hours
User Story | Task | Member responsible for the task | Task Assigned to | Estimated Effort (in hours per person) | Priority (A-E)
User wants to add a new activity | Make a scene for the category and adding activities | jahson | kamron | 2 | B
User wants to have a nice main page | Build a nice main screen with the rings | kamron | jahson | 3 | B
User wants profile menu | create a profile menu | vlad | vlad | 7 | D
User wants to click and send some information to the server | Create the communication client —server | julius | julius | 4 | B
User to add features (database side) | Create the database functionalities to add all features | paul and pablo | paul and pablo | 6 | B